## SUM DMO
Item ID | SIDE | Item Description | Status | Responsible | Owner | Due Date | Comments MP1 | Comments DRY RUN | Comments QAS | Comments DEV | Comments SBX
1 | MP1 | Stop SAP services on source system | Completed | Sonia | Sonia | 2026-05-15 | Services stopped successfully
2 | MP1 | Export database backup | In progress | Alex | Alex | 2026-05-15 | Backup completed at 14:30
3 | MP1 | Run SUM DMO pre-checks | Completed | Sonia | Sonia | 2026-05-16 | Pre-checks running
4 | QAS | Execute transport requests | Open | Silvia | Silvia | 2026-05-17 |  |  | QAS transports pending
5 | MP1 | Validate data migration | Open | Maria | Maria | 2026-05-18 | Critical step - validate all data
6 | DEV | Configure target system parameters | Not Ok | Bogdan | Bogdan | 2026-05-19 |  |  |  | DEV config pending
7 | MP1 | Run post-migration tests | Open | Maria | Maria | 2026-05-20 | Full regression test needed
8 | MP1 | Start SAP services on target system | Open | Silvia | Silvia | 2026-05-20 | Final step

## SAP User Access List
Team | Name | Email | QX-User ID | Needed Authorizations (source) | Needed Authorizations (target) | Comment | Access tested on MP1 source
Basis | Sonia | sonia.frumuseanu@sap.com | Sonia | SAP_ALL; S_BTCH_ADM | SAP_ALL; S_BTCH_ADM | System admin | Yes
Functional | Alex | mihai.vornicu@sap.com | Alex | Z_BACKUP_ROLE | Z_RESTORE_ROLE | DBA team | Yes
Basis | Maria | maria.bistreanu@sap.com | Maria | S_BTCH_ADM; Z_SUM_ROLE | S_BTCH_ADM; Z_TARGET_ROLE | SUM specialist | Yes
Apps | Silvia | silvia.neacsu@sap.com | Silvia | Z_TRANSPORT_ROLE |  | Transport manager | No
Basis | Bogdan | mihai.vornicu@sap.com | Bogdan | Z_CONFIG_ROLE | Z_CONFIG_TARGET | Config specialist | No

## Summary
Status | Count
Completed | 2
In progress | 1
Open | 4
Not Ok | 1